## Slide 1
Start Sprint2018PI-2.4
Complete CICD environment set up and integration with SonarQube and Selenium
Continue Centralized Eligibility Repository development
Continue UX design for new GUI screens
Continue lower environment build (ETC in May)
Prepare OSAM capability health assessment action plan
Complete EIS assessment
Provide metrics (latency numbers) to OARB
Planned for Next Period
Progress This Period
Completed Sprint2018PI2.3
CICD environment set up and integration with Jenkins, Maven, GitHub and Docker is complete; SonarQube and Selenium are in progress
Completed ALDON/ACMS release “ELG” for centralized eligibility
Completed OSAM capability health assessment
UX design for new GUI screens is in progress – completed prototype and style guide
Lower environment build in progress
Key Decisions/ Risks
Financial Updates
  2018 ACAP: $2M (includes $150K Hardware)
  2018 Actuals $288,658 (14%)
Eligibility RxClaim Modernization - Centralized Eligibility
Zerafa (S)
Cattran (O)
Acosta (PM)
Status:
Last Updated 4.25.2018
Onshore/Offshore overlap hours – only 1 hour overlaps
  Mitigate: Team members adjusting working hours to adjust overlapping availability
Key Milestones |  |  |  |  | 
Milestone Chart | Start Date | End Date | % Complete | Status | Comments
Complete Requirements / Analysis |  | 6/30/17 | 100% | C | 
Build Development Environment |  | 1/31/18 | 100% | C | 
Complete Solution SID |  | 3/27/18 | 100% | C | 
Build Development Team |  | 03/19/18 | 100% | C | 
Agile Training |  | 03/16/18 | 100% | C | 
Agile Mobilization |  | 1/26/18 | 100% | C | 
Run Agile Sprint 0 | 1/16/18 | 1/26/18 | 100% | C | 
Run Agile Sprint 1 | 1/31/18 | 2/14/18 | 100% | C | 4 stories (29 story points)
Run Agile Sprint 2 | 2/14/18 | 2/28/18 | 100% | C | 5 stories (31 story points)
Run Agile Sprint 3 | 3/1/18 | 3/14/18 | 100% | C | 10 stories (25 story points)
Run Agile Sprint2018PI-2.1 | 3/15/18 | 3/28/18 | 100% | C | 9 stories (7 story points)
Run Agile Sprint2018PI-2.2 | 3/29/18 | 4/11/18 | 100% | C | 4 stories (16 story points)
Run Agile Sprint2018PI-2.3 | 4/12/18 | 4/25/18 | 100% | C | 11 stories (21 story points) 4 spike stories 7 dev stories 4 stories from last sprint
Run Agile Sprint2018PI-2.4 | 4/26/18 | 5/9/18 | 0% | G | 18 stories (23 story points) 16 dev stories 2 spike stories
Run Agile Sprint …to 2.5 then start with 3.1 |  |  | 0% |  | 
Build Production Environment |  | 6/1/18 | 0% |  | Production system infrastructure will be needed in late Q2. Engage for new estimates after final solution.
Server Provisioning |  | 6/1/18 | 0% |  | Date is TBD
Deploy to Production |  | 9/30/18 | 0% |  | Date is TBD Multiple deployments Phase 1 in late Q3 early Q4 2018
Complete Final Go-Live |  | Q1 – Q2 2019 | 0% |  | Date is TBD due to delay in starting, Target late Feb to Apr 2019

## Slide 2
Eligibility RxClaim Modernization - Centralized Eligibility
Zerafa (S)
Cattran (O)
Acosta (PM)
Status:
Last Updated 4.25.2018
 | 2018 |  |  |  | 2019 |  |  | 
Milestone | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1st - Build Centralize Eligibility Database: |  |  |  |  |  |  |  | 
Identify eligibility related tables, indexes, displays and programs (core & custom - BK1/BK2) | l | l |  |  |  |  |  | 
Identify daily, weekly, monthly ROBOT/TWS job |  | l |  |  |  |  |  | 
Modernize Eligibility database (convert decimal Date/Time with true Date/Time) | l |  |  |  |  |  |  | 
Enhance carrier or carrier extension table to include "Instance ID" | l |  |  |  |  |  |  | 
Identify and partition large tables like MEL, AMD, etc. | l |  |  |  |  |  |  | 
Convert roll logic to SQL triggers that move inactive records to history tables | l |  |  |  |  |  |  | 
Build lower [SYS/INT, QA & UAT] environments: |  |  |  |  |  |  |  | 
IBM i Partition [re purpose existing partition - RxMCMTST] |  | l |  |  |  |  |  | 
Webspher/App/Cloud Servers |  | l |  |  |  |  |  | 
Install MQ/MQFTE to support BK2 NRT |  | l |  |  |  |  |  | 
Build connectivity for PEER, ERA, Ab Initio, sterling integrator, etc. |  | l | l |  |  |  |  | 
Engage Secure and access admin for user provisioning |  | l | l |  |  |  |  | 
Build MIMIX Share AKA Double-Take data replication model from centralized eligibility to respective RxCLAIM instances |  | l |  |  |  |  |  | 
Build Web Service that replicate dynamic enrolment changes from all RxCLAIM instances to centralized eligibility |  | l | l |  |  |  |  | 
Build data compare utility or Audit data between RxCLAIM instances and Centralize eligibility |  | l | l |  |  |  |  | 
Convert RxCLAIM eligibility screens to read-only |  | l | l |  |  |  |  | 
Production Deployment / Roll-out |  |  |  |  |  |  |  | 
Perform Performance Testing |  |  |  |  |  |  |  | 
Eligibility Stage/Load |  |  |  | l |  |  |  | 
MIMIX Share data replication |  |  |  | l |  |  |  | 
Web/GUI application |  |  |  | l |  |  |  | 
Data migration strategy and migrate historical data from all RxCLAIM instances to Centralize eligibility |  |  |  | l |  |  |  | 
Install, configure & schedule Stage/Load process for Member & Group Eligibility (core & custom - BK1/BK2) and other ROBOT/TWS jobs |  |  |  | l |  |  |  | 
Configure MIMIX Share data replication model |  |  |  | l |  |  |  | 
Install, configure & schedule data compare utility / audit data between all RxCLAIM instances and centralize eligibility |  |  |  | l |  |  |  | 
Convert RxCLAIM eligibility screens to read-only to all RxCLAIM instacnes |  |  |  | l |  |  |  | 
Role out solution to all RxCLAIM instances (13+), Post Production go-live monitoring and Support |  |  |  |  | l | l |  | 
 | 2018 |  |  |  | 2019 |  |  | 
Milestone | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
2nd - Design & Build Web GUI |  |  |  |  |  |  |  | 
Design & Build Web base interface/GUI application |  | l | l | l |  |  |  | 
Design & Build security framework |  | l | l | l |  |  |  | 
Define roles in Optum ID, tied to GUI page access |  |  | l | l |  |  |  | 
Define client in Optum ID, tied to row-level access (eliminate the use of client logical views) |  |  | l | l |  |  |  | 
Protect SSN been displaying on GUI page |  |  | l | l |  |  |  | 
Build centralize dash board (end to end process view) |  |  |  |  |  |  |  | 
In coming eligibiilty file status, Pend, In Process, Pass, Fail |  |  | l | l |  |  |  | 
Archieve incoming eligibility file and associated load reports |  |  | l | l |  |  |  | 
Archieve auditing data |  |  | l | l |  |  |  | 
View online and the archieved incoming eligibility files and associated load reports |  |  | l | l |  |  |  | 
Combined view of on/off system storage and data |  |  | l | l |  |  |  | 
Production Deployment / Roll-out |  |  |  |  |  |  |  | 
Deploy / roll-out Web GUI |  |  |  |  | l |  |  | 
Configure user/client access as solution roll-out to each RxCLAIM instances |  |  |  |  | l | l |  | 
3rd - Web Service/API |  |  |  |  |  |  |  | 
Build Microservices (Web Service/API) for eligibility & claim lookups |  |  |  | l |  |  |  | 
Repoint all external API/Web Service which is to start consuming Centralize Eligibility Data |  |  |  | l |  |  |  | 
Production Deployment / Roll-out |  |  |  |  |  |  |  | 
Deploy / roll-out solution |  |  |  |  |  | l |  | 
Deprecate RxCLAIM eligibility screens |  |  |  |  |  | l |  | 
Suspend data replication from centralize elig to RxCLAIM instances |  |  |  |  |  | l |  | 
Notes: Amy – to talk through delays in technology deliveries
Melissa – to talk through impact to TFN and Agent Migrations